# Sprint One Report

Portfolio task 4

Unit code: COS40005 EAT40005

Unit Name: Engineering project A

Submission date:

[This is a template, remove any text within third brackets before submission]

| Student Name | Student Id | Statement of contribution to the report |
| --- | --- | --- |
| Ashim Adhikari | 104104333 |  |
| Aaradhya Lamsal | 103828166 |  |
| Ruffin Remad | 103840173 | Developed design and implementation as part of the sprint, reviewed key lessons learned and further improvements |
| Nur E Siam | 103842784 |  |
| Shivam Sharma |  |  |
| Ankit Malik |  |  |
| Prabesh Bhattarai | 104085535 | Sprint plan (sprint 1, 2 and 3) |

## Acknowledgment of Country

[Add a statement on acknowledgment of the country.]

Each team member identifies:

- the Traditional Owners of the land they lived on while completing this work (if living in Australia)…

## PRoduct backlog(ANKIT)

| ID | Task/Feature | Description | Business Value (Priority) | Dependencies | Planned Sprint |
| --- | --- | --- | --- | --- | --- |
| 1 | User Registration and Login | Enable users to register, log in, and reset passwords using email/phone. | High | None | Sprint 2 |
| 2 | Profile Management | Allow users to update personal details, including contact info, preferences, and professional verification status. | High | User Registration and Login | Sprint 2 |
| 3 | Property Listings | Users can create property listings with details like property type, location, price, and images. | High | User Registration and Login | Sprint 1 |
| 4 | Search and Filtering | Enable advanced search with filters for location, price, property type, and amenities. | High | Property Listings | Sprint 1 |
| 5 | Interactive Map-based Search | Integrate Google Maps for proximity-based search to allow users to search properties by area or key landmarks. | High | Search and Filtering, Google Maps API | Sprint 2 |
| 6 | Property Listing Management | Allow users to edit or delete their own listings and track listing performance. | Medium | Property Listings | Sprint 2 |
| 7 | Messaging System | Implement secure in-app messaging for communication between users and real estate professionals. | High | User Registration and Login | Sprint 3 |
| 8 | Notifications | Real-time notifications for new messages, updates on listings, or system alerts. | Medium | Messaging System, Property Listings | Sprint 3 |
| 9 | Multi-language Support | Enable platform localization with support for Bengali and English. | Medium | UI/UX Design | Sprint 3 |
| 10 | Secure Data Encryption | Implement data encryption for sensitive information (AES-256 and TLS). | High | None | Sprint 3 |
| 11 | System for Verification Professionals | Implement multi-factor authentication and CAPTCHA to verify real estate professionals and ensure authenticity. | High | User Registration and Login | Sprint 4 |
| 12 | User Reviews and Ratings | Allow users to rate and review properties and professionals after interactions. | Medium | Property Listings, Profile Management | Sprint 4 |
| 13 | Image Upload Optimization | Automate image compression upon upload and optimize media storage using AWS S3. | Medium | Property Listings, AWS S3 | Sprint 4 |
| 14 | Appointment Scheduling | Implement a system for scheduling property visits and viewing times with reminders. | Medium | Messaging System, Property Listings | Sprint 4 |
| 15 | Analytics and Reporting for Admin | Provide admin with analytics and reporting on user activities, property listings, and professional verifications. | Low | User Registration, Property Listings | Sprint 5 |
| 16 | Admin Dashboard | Develop an admin dashboard for managing users, content moderation, and reporting. | Medium | Admin System, Analytics and Reporting | Sprint 5 |
| 17 | Backup and Recovery | Implement automated backups and recovery procedures using AWS RDS and S3. | High | Database Setup (Amazon RDS) | Sprint 5 |
| 18 | Scalability (Auto Scaling & Load Balancing) | Implement auto-scaling and load balancing to handle traffic spikes during peak periods. | High | AWS Setup, Backend Infrastructure | Sprint 5 |

## QUality plan(Shivam)

[Describe the target quality expectation of the deliverables, steps to assure quality, planned testing etc.]

The quality plan is essential to ensure that the real estate platform meets the functional, performance, security, and user experience requirements of the project. The goal is to deliver a high-quality product that addresses the specific needs of the Bangladeshi real estate market, ensuring user satisfaction and platform reliability. This plan outlines the target quality expectations, quality assurance processes, and the steps that will be taken to test and validate the system.

#### 1. Target Quality Expectations

The following quality expectations have been set for the project:

- Reliability: The platform should have an uptime of at least 99.5%, ensuring that the system is available for users, especially during peak hours, such as the start of the academic year when students search for rental properties.

- Performance: The system should maintain fast load times (under 2 seconds) for key features like property search and messaging, even under high traffic (up to 10,000 concurrent users).

- Security: Data security is critical due to sensitive information (user profiles, professional verification, property listings). The platform must comply with industry-standard encryption (AES-256 and TLS) and undergo regular vulnerability testing to protect against security threats.

- Scalability: The system should scale dynamically to handle traffic spikes, ensuring seamless performance without downtime.

- User Experience: The platform should be easy to navigate, with intuitive search and filtering functions, multi-language support (Bengali and English), and responsive design for both web and mobile interfaces.

- Functionality: All core functionalities (e.g., user registration, property listings, messaging, and notifications) should work seamlessly, and user inputs must be validated effectively to prevent errors or incorrect data entry.

- Accuracy and Trust: The platform should implement a robust verification system for real estate professionals, ensuring that users trust the information provided.

#### 2. Quality Assurance Process

To meet the quality expectations outlined above, the following steps will be taken to assure quality throughout the project:

##### 2.1 Code Quality and Best Practices

- Code Reviews: Each piece of code will undergo peer reviews to ensure it adheres to best practices, such as proper use of functions, modularity, and clear naming conventions.

- Linting and Formatting: Tools like ESLint for JavaScript and Prettier for formatting will be used to maintain a consistent codebase and identify any potential issues early.

- Version Control: Git will be used to manage version control, with code changes pushed through a pull request process. This will ensure that all changes are reviewed and approved before being merged into the main branch.

##### 2.2 Automated Testing

- Unit Testing: Automated unit tests will be written using frameworks like Jest for React.js and Node.js. Unit tests will cover critical components such as user registration, property listings, search functionality, and messaging.

  - Objective: Ensure that each component behaves as expected under different conditions.

  - Target: Achieve 90% test coverage of the codebase.

- Integration Testing: Integration tests will verify that different components of the platform work well together, such as ensuring property listings integrate properly with the search and messaging systems. Tools like Postman and Cypress will be used for API and frontend integration tests.

  - Objective: Confirm that various parts of the system (e.g., backend and frontend) interact as expected.

- End-to-End (E2E) Testing: E2E tests will simulate real-world user scenarios, testing entire workflows such as registering, logging in, searching for properties, and messaging an agent. Tools like Selenium or Cypress will be used for this purpose.

  - Objective: Validate the full user journey to ensure a seamless experience.

  - Target: Ensure critical user journeys (such as property search, messaging, and login) are fully functional.

##### 2.3 Manual Testing

- User Acceptance Testing (UAT): Before deployment, user acceptance testing will be conducted to verify that the platform meets user expectations. Real users (students, property buyers, agents) will test key features to ensure usability, functionality, and trust.

  - Objective: Ensure the platform meets the needs of the Bangladeshi real estate market and delivers a good user experience.

  - Feedback: User feedback from UAT will be analyzed, and necessary changes will be implemented in the next sprint.

##### 2.4 Security Testing

- Penetration Testing: External penetration testing will be performed to identify and address any vulnerabilities, such as SQL injection or cross-site scripting (XSS).

- Data Encryption Validation: Tests will verify that sensitive information (passwords, personal details) is encrypted using AES-256 and TLS protocols.

  - Objective: Ensure data security and compliance with privacy regulations.

##### 2.5 Performance and Load Testing

- Load Testing: Tools like Apache JMeter or Loader.io will be used to simulate high traffic (up to 10,000 concurrent users) to ensure the platform can handle peak loads.

  - Objective: Validate system performance and ensure response times remain under 2 seconds for 95% of the transactions.

- Scalability Testing: AWS auto-scaling features will be tested to ensure that additional resources are provisioned automatically during traffic spikes.

  - Objective: Ensure the platform can dynamically scale to handle increased user demand.

##### 2.6 UI/UX Testing

- Usability Testing: Regular usability tests will be conducted to assess the user experience, ensuring that navigation is intuitive and responsive. Tools like Hotjar or UserTesting.com will help monitor user interactions and feedback.

  - Objective: Ensure the platform is easy to use and navigate, providing a positive experience for both tech-savvy and non-tech-savvy users.

  - Multi-Language Testing: The platform’s localization (Bengali and English) will be tested to ensure all text is displayed correctly and contextually in both languages.

#### 3. Planned Testing Stages

Testing will occur throughout the development process, integrated into each sprint cycle to ensure that bugs are caught early, and features are validated as they are developed.

##### 3.1 Sprint 1: Basic Features Testing

- Unit Testing: Focus on user registration, login, and profile management.

- Integration Testing: Ensure registration connects properly with user profiles.

##### 3.2 Sprint 2: Search and Map Testing

- Unit and Integration Testing: Validate property listings and search functionality.

- End-to-End Testing: Test the interactive map and filtering features with real-time data.

##### 3.3 Sprint 3: Messaging and Notification Testing

- Unit and Integration Testing: Ensure real-time messaging and notifications are working across different user roles (buyers, sellers, agents).

- Performance Testing: Begin load testing with moderate traffic levels (up to 5,000 concurrent users).

##### 3.4 Sprint 4: Security and Verification Testing

- Security Testing: Focus on penetration tests, CAPTCHA, and multi-factor authentication.

- Data Encryption Testing: Verify that sensitive information is properly encrypted.

##### 3.5 Sprint 5: Full System Testing

- End-to-End Testing: Simulate complete user journeys across all features, ensuring all components (messaging, search, registration) work seamlessly together.

- Performance and Load Testing: Test the platform’s scalability with up to 10,000 concurrent users.

#### 4. Continuous Integration (CI) and Continuous Deployment (CD)

The project will use a CI/CD pipeline to ensure that code changes are automatically tested and deployed. GitHub Actions or Jenkins will be used to automate the following processes:

- Code Integration: Automatically run unit and integration tests on every commit or pull request.

- Automated Deployment: Successful builds will be deployed to the testing environment for further evaluation and feedback.

## SPrint PLAN (ASHIM/ PRABESH)

[Describe the number of sprints you plan to execute to complete the project. The first sprint is going to be from week 9 to week 11 in semester 1. There will be four more sprints next semester (Sprint 2 week 1- 3, Sprint 3 week 4-6, Sprint 4 week 7-9, and Sprint 5 week 10-12). The project needs to be completed within the five sprints. A detailed timeline is expected to be presented here, graphical representations are welcome.]

- Sprint 1: Initial Design, Architecture Setup, and Prototyping

Timeline: Semester 1, Weeks 9-11

Goal: Create a solid foundation with architecture and initial prototypes for the real estate application.

- Week 9:

- Finalize project roadmap.

- Develpment of front-end page with buy, rent, and sold, pages.

- Add fully working search functions to the webpage for searching properties.

- Week 10:

- Set up AWS backend environment (AWS Amplify).

- Deploy the code in AWS cloud and test the connectivity.

- Week 11:

- Finalize basic UI prototypes for web application with at least 1-2 function working

- Add a basic google map and pinpoint the location of the properties in the map.

- Integrate the frontend prototype with AWS backend to access the page public form any geographical region with internet access.

Deliverables: Project roadmap, architecture, basic UI prototype, AWS environment setup.

- Sprint 2: Backend Development and Core Functionality Implementation

Timeline: Semester 2, Weeks 1-3

Goal: Implement core backend functionalities, focusing on security, user authentication, and media management.

- Week 1:

- Finalize database schema using MySQL on AWS RDS.

- Start backend logic with AWS services functions for property listings management.

- Week 2:

- Set up secure user authentication using AWS Cognito.

- Enable two-way multi-factor authentication using OTP code via email or phone while singing in.

- Configure AWS S3 for media storage (images, videos), and connect it to the backend.

- Week 3:

- Integrate Interactive map-based search for some popular cities of Bangladesh where many colleges and universities are located.

- Start working on basic mobile application user interface and choosing appropriate colour scheme.

Deliverables: Database setup, media management, and database integration.

- Sprint 3: Real-Time Interaction, Frontend Enhancement and security enhancement

Goal: Enable real-time interaction, improve the frontend, and add location-based services like map integration.

- Week 4:

- Implement real-time messaging using WebSocket for communication between users and professionals.

- Continue frontend integration with ReactJS for web and mobile apps.

- Week 5:

- Test real-time messaging and property search functionalities.

- Enhance frontend for responsive design across different screen sizes and devices.

- Make good user interface to view property details. This interface will show property features including amenities.

- Week6:

- Implement ACLs for configuring basic security measure during development phase of sprint 3.

- Configure basic settings for AWS WAF (Web Application Firewall) to analyse security settings.

Deliverables: Real-time messaging, responsive and optimized frontend and security enhancement.

4.    Sprint 4: Security Implementation, Testing and Database Setup 
            Timeline: Semester 2, Week 7-9
               
             Goal: Implement security features, conduct initial testing, and set up the database

infrastructure for the real estate application.

Week 7:

Integrate AWS WAF for web application security against SQL Injection and XSS attacks.

- Set up and configure Amazon Cognito for user authentication with MFA.

- Implement access control mechanisms for different user roles (e.g., Admin, Property Owner, User).

Week 8:

- Deploy Amazon RDS for database management and ensure high availability using multi-AZ deployment.

- Conduct security tests focusing on firewall rules, access control, and user authentication.

- Set up logging and monitoring services using Amazon CloudWatch for security and performance insights.

Week 9:

- Optimize network security by configuring subnets, security groups, and NACLs within the VPC.

- Perform security and performance benchmarking using automated testing tools.

- Review security implementation, conduct peer reviews, and document test cases and results.

Deliverables:

- Security features (AWS WAF, Cognito) integrated.

- RDS setup and tested.

- CloudWatch monitoring configured.

- Security tests completed and documented.

Sprint 5: Load Balancing, Scalability, and Final Testing

Timeline: Semester 2, Weeks 10-12

Goal: Ensure scalability, conduct final testing, and refine the application for deployment.

Week 10:

- Set up Amazon Route 53 for DNS routing with health checks for load balancing.

- Configure Amazon CloudFront for content delivery and performance optimization.

- Test load handling using AWS Elastic Load Balancer (ELB) across multiple Availability Zones.

Week 11:

- Implement NAT Gateway and Internet Gateway for secure internet access to instances.

- Optimize the caching mechanisms for faster content delivery using CloudFront.

- Conduct load testing to ensure the application can handle peak traffic without downtime.

Week 12:

- Complete the integration of SNS for event-driven notifications (e.g., new property listings, system alerts).

- Final round of end-to-end testing, covering performance, security, and scalability.

- Review and finalize documentation for all AWS services used and their configurations.

Deliverables:

Route 53 and ELB configured.

CloudFront and caching optimized.

Load testing completed.

Final testing report and system documentation ready for deployment.

## Sprint one review (Critical review of the product)(SiAM)

[Add a detailed report on the following

- Sprint 1 plan (deliverables agreed with the client/supervisor)

- Progress made in the first sprint (description with screenshots)

- Feedback received from the client on the deliverable (must indicate if the increment was deliverable or not)

- A critical analysis of progress against the plans, particular progress achieved, challenges faced etc. for the deliverable]

##### Planned Deliverables for Sprint 1

The key deliverables for Sprint 1 were:

- User Registration and Login: Enable users to register, log in, and reset their passwords.

- Profile Management: Allow users to create and manage profiles.

- Property Listings (Basic): Allow users to create property listings with essential details such as type, location, and price.

- Initial Backend Setup: Develop the backend infrastructure to support user data and property management.

#### Progress Achieved

- User Registration and Login:

  - Progress: The user registration and login functionality was partially implemented. The team was able to create a basic registration form with validations for email and phone number. However, since the backend was not developed, data could not be stored or processed.

  - Achievements:

    - A working frontend form for user registration was created and validated.

    - Basic UI flow from registration to login was completed, though these features are not functional due to the absence of a backend.

  - Challenges: Without the backend, the user registration system could not store credentials or enable login functionality.

  - Next Steps: Backend development will be prioritized in Sprint 2 to make this feature fully functional.

- Profile Management:

  - Progress: Profile management was not implemented in Sprint 1 due to the lack of backend infrastructure. Users cannot yet update their personal details or preferences.

  - Challenges: The absence of a backend made it impossible to store or manage profile data.

  - Next Steps: Once the backend is developed in Sprint 2, profile management will be implemented. This will include setting up user databases to store and retrieve personal details.

- Property Listings (Basic):

  - Progress: The basic property listing feature was partially implemented. The team designed a form for property listing creation on the frontend, but without a backend, property data could not be stored or retrieved.

  - Achievements:

    - A frontend form was created where users can input property details like type, price, and location.

  - Challenges: Similar to registration, the lack of a backend prevented the platform from storing or displaying listings.

  - Next Steps: Backend development in Sprint 2 will enable the property listing feature to become functional. This will include creating a database to store listings and implementing data retrieval for users.

- Initial Backend Setup:

  - Progress: The backend was not developed in Sprint 1. The team faced time constraints and technical challenges that delayed the setup of a backend architecture (e.g., database configuration and server-side logic).

  - Challenges: The lack of backend infrastructure significantly impacted other planned features, such as user registration, profile management, and property listings.

  - Next Steps: Backend development will be the primary focus of Sprint 2, with the team setting up the database (AWS RDS or MySQL), building server-side logic (Node.js or another backend framework), and linking it to the frontend.

#### Challenges Faced

- Backend Development Delays:

  - Problem: The team did not develop the backend in Sprint 1 due to time constraints and prioritization issues.

  - Impact: Without the backend, features like user registration, profile management, and property listings remained incomplete and non-functional.

  - Plan: Backend setup will be a top priority for Sprint 2. The team will focus on building a database to store user data and property listings and implementing server-side logic to manage these functions.

- Limited Progress on Profile Management:

  - Problem: Since there was no backend, the team could not implement profile management in Sprint 1.

  - Impact: Users are currently unable to update their personal details or manage their profiles.

  - Plan: Profile management will be revisited in Sprint 2 after the backend is ready, ensuring user data can be stored and retrieved effectively.

- Dependencies on Backend for Property Listings:

  - Problem: While the frontend form for property listings was created, the feature remained incomplete due to the absence of backend support.

  - Impact: Users cannot yet create, edit, or view property listings.

  - Plan: Once the backend is developed, property listings will be made fully functional. The team will also focus on integrating the AWS S3 service for image uploads.

#### Progress vs. Planned Deliverables

- Successes:

  - The frontend components for user registration and property listings were partially implemented, giving the team a strong visual foundation.

  - The UI flow for user registration, login, and property listings was designed and integrated with basic validations.

- Incomplete Deliverables:

  - Backend Development: The absence of backend development impacted all key features, leaving registration, profile management, and listings non-functional.

  - Profile Management: Since this is dependent on the backend, no progress was made on this feature in Sprint 1.

#### Lessons Learned

- Prioritize Backend Development: A critical lesson from Sprint 1 is the importance of developing the backend early in the project to support core functionalities like registration and data storage.

- Time Management: Better time allocation and planning are required to ensure that both frontend and backend development progress in parallel.

- Communication and Task Delegation: More effective delegation of tasks and communication will help the team avoid bottlenecks and ensure all critical features are developed on time.

## Retrospect (Critical review of the process)(AAradhiya)

Using an organized methodology, our team broke the project up into three primary sprints, each with a prep and wrap-up phase. Our objectives could be regularly reevaluated and developed iteratively thanks to this framework.

Key aspects of our process:

- Weekly gatherings to talk about achievements and difficulties

- Using SharePoint for document management and Microsoft Teams for collaboration

- Precise descriptions of roles based on personal strengths

- Continual revisions to user stories and project backlogs

Throughout the sprints, we encountered several challenges:

- Part-time Availability: Different schedules among team members made collaboration challenging.

Solution: Expanded the usage of asynchronous communication tools and instituted flexible meeting schedules.

- Skills Gaps: A few team members lacked project-related knowledge of technologies.

Solution: Set up peer-learning meetings and made use of internet tools to improve skills.

- Technical Complexity: A few project features required sophisticated implementations.

Solution: Allotted more time for extensive study and feature prototyping.

- Project Scope Management: It was difficult to strike a balance between the deadlines for features and development.

Solution: To efficiently manage jobs and modify scope as needed, a priority matrix was implemented.

Sprint-specific Observations

SPRINT 1

- Focus on requirement engineering and initial development

- Challenge: Aligning on technical architecture decisions

- Outcome: Successfully established our core infrastructure

SPRINT 2

- Emphasis on user-centered design and core feature development

- Bottleneck: Integrating third-party APIs with our services

- Resolution: Conducted focused technical spikes to resolve integration issues

SPRINT 3

- Concentrated on risk management, quality assurance, and communication

- Challenge: Balancing bug fixes with new feature development

- Approach: Implemented a priority matrix to manage tasks effectively

Key Learnings and Improvements

- Documentation: Improved our documentation process for better team alignment.

- Task Prioritization: Developed a more effective system for prioritizing and managing tasks.

- Communication: Enhanced our communication protocols to ensure all team members stayed informed.

- Retrospectives: Started conducting end-of-sprint retrospectives to continuously improve our process.

Though we confronted and overcame substantial hurdles relating to part-time availability, talent inequalities, and project complexity, our organized approach gave us a strong foundation for development. As the project progressed, our capacity to modify our procedures was essential, especially in the areas of task management and information exchange. Going forward, we want to increase communication, continue to cultivate a culture of continuous learning and improvement within the team, and further refine our development techniques.

## Lessons learned (Critical review of SPRINT one experience and future plan) (Ruffin)

1. Critical review of Sprint 1 experience:

- Milestones

- Foundations Laid: The core architecture was established using AWS services, ensuring a scalable backend infrastructure. The frontend was developed with key pages, including home, rent, and sold property pages. Additionally, deploying the site on the cloud through AWS Amplify allowed public access, setting the stage for further development and testing.

- Team Collaboration: The team effectively used Microsoft Teams for communication and SharePoint for document management, ensuring smooth coordination. Weekly meetings allowed members to track progress and address challenges, while tasks were assigned based on individual strengths. Although communication was generally effective, better alignment on task dependencies will be prioritized in future sprints.

- Progress of Implementation: Significant progress was made on the frontend, including the implementation of search and filtering features. The Google Maps API was integrated, enabling users to search properties by location. However, backend delays prevented some features, like user registration, from being fully functional during this sprint.

- Challenges

- Technical Complexities: Integrating AWS services and the Google Maps API was more challenging than anticipated, leading to some delays. Configuring authentication and ensuring the seamless connection between frontend and backend components required additional effort. These issues highlighted the need for earlier technical planning and testing.

- Time Management: Conflicting schedules among team members made it challenging to align tasks effectively. Delays in backend development affected dependent features, slowing overall progress. Moving forward, better time management strategies, including parallel development of frontend and backend, will be implemented.

- Learning Curves: Team members faced challenges in working with new tools, including AWS Amplify and Google Maps API, which initially slowed development. Peer learning sessions and external resources were used to build competence with these technologies. This experience reinforced the importance of continuous learning and skill sharing within the team.

- Lessons Learned

- Early Risk Management: Identifying and mitigating potential risks early is critical, especially when working with external APIs and cloud infrastructure. A more comprehensive risk assessment during the initial planning phase could have minimized delays. Moving forward, the team will conduct detailed risk evaluations at the start of each sprint to anticipate challenges and develop mitigation strategies.

- Importance of Agile Adaptation: The ability to adapt to changing priorities and unforeseen challenges proved essential during this sprint. Agile practices, such as reprioritizing tasks and reallocating resources, enabled the team to stay on track despite delays. This flexibility will remain a core part of the team's approach in future sprints to ensure continued progress.

- Continuous Communication: While the team used effective communication tools, occasional gaps impacted task coordination. More frequent check-ins, particularly during critical phases, will be implemented to prevent misalignment. Moving forward, the team will enhance both synchronous and asynchronous communication to ensure that everyone stays informed and aligned.

2.  Future Plan

- Goals for Sprint 2

- Core Feature Development: Focus on completing backend development using MySQL on AWS RDS to store user data and property listings. This will ensure smooth data management and allow for essential functionalities like property listings, search, and user profiles to work seamlessly.

- Backend database: Develop secure backend logic using AWS Cognito for authentication with multi-factor authentication (MFA) to enhance security. Integration of user registration, login, and profile management will be a priority, ensuring that the platform is ready for user onboarding.

- Mobile app development: Begin the design and development of the mobile version of the platform using React Native or a similar framework. The goal is to ensure the mobile app mirrors the web version's features, providing a consistent and intuitive experience for users across devices.

- Improvements to Development Process

- Enhanced Sprint Planning: Break down tasks into smaller, actionable components to improve task tracking and completion. Allocate buffer time for complex tasks involving API integrations or cloud services to handle unexpected challenges efficiently. Use continuous integration pipelines to streamline deployment and testing processes, reducing the risk of last-minute issues.

- Task Management and Communication: Implement more frequent check-ins and status updates to prevent miscommunication or delays. Use project management tools like Trello or Jira to ensure all tasks are assigned, tracked, and updated in real-time.

- Long-term Outlook

- Scaling for Future Sprints: Set up AWS auto-scaling and load balancing to handle traffic surges and ensure system reliability under varying loads. Use AWS CloudWatch for performance monitoring, providing real-time insights into system health and enabling proactive issue resolution.

- User Feedback: Collect feedback from early users to identify pain points and improve features such as property search and Google Maps integration. Use this feedback to refine the user experience and ensure the platform meets the needs of the Bangladeshi real estate market effectively.